## Project Tracking
Project Start Date | 2024-03-20 |  |  | Project End Date | 2024-04-28 | Cost (per 60 min) | 25
| Student Name | Duration (Min) | % Complete | Subtotal Minutes | Subtotal Cost
Milestone 1
Read Case + Prepare Questions for client | Andrew | 20 | 100 | 20 | 8.3333
Read Case + Prepare Questions for client | Alexander | 20 | 100 | 20 | 8.3333
Read Case + Prepare Questions for client | Simra | 30 | 100 | 30 | 12.5
Read Case + Prepare Questions for client | Kendall | 25 | 100 | 25 | 10.4167
Client Meeting | Everyone | 15 | 100 | 60 | 25
ERD Design | Alexander | 60 | 100 | 60 | 25
ERD Design | Simra | 80 | 100 | 80 | 33.3333
Assumptions | Everyone | 15 | 100 | 15 | 6.25
Write-up preparation | Andrew | 90 | 100 | 90 | 37.5
Write-up preparation | Alexander | 70 | 100 | 70 | 29.1667
Write-up preparation | Kendall | 40 | 100 | 40 | 16
Write-up preparation | Simra | 60 | 100 | 60 | 25
Sub Total |  |  |  | 570 | 237.5
Milestone 2
Write-up preparation | Alexander | 120 | 80 | 120 | 50
Normalization relationships | Simra | 120 | 100 | 120 | 50
Write-up preparation | Kendall | 60 | 100 | 60 | 25
Redesigning ERD | Alexander | 60 | 100 | 60 | 25
Write-up preparation | Andrew | 45 | 100 | 45 | 18.75
Sub Total |  |  |  | 405 | 168.75
Milestone 3
Data Dictionary | Alexander | 120 | 100 | 120 | 50
Write-up preparation | Alexander | 70 | 100 | 70 | 29.1667
Client Presentation | Everyone | 20 | 100 | 80 | 33.3333
Physical Design | Alexander | 120 | 25 | 120 | 50
Physical Design | Simra | 120 | 50 | 120
Physical Design | Andrew | 240 | 100 | 240 | 100
Physical Design | Kendall | 120 | 100 | 120 | 50
Creating Query | Kendall | 90 | 85 | 90 | 38
Creating Query | Alexander | 70 | 50 | 70 | 29.1667
Creating Query | Andrew | 180 | 100 | 180 | 75
Client Meeting | Everyone | 30 | 100 | 30 | 12.5
Sub Total |  |  |  | 1240 | 516.6667
Final Submission
Write-up preparation | Andrew | 60 | 100 | 60 | 25
Write-up preparation | Alexander | 70 | 100 | 70 | 29.1667
Fixing Query | Andrew | 120 | 100 | 120 | 50
Fixing Query | Alexander | 120 | 100 | 120 | 50
Fixing Query | Simra | 120 | 100 | 120 | 50
Fixing Query | Kendall | 120 | 100 | 120 | 50
Sub Total |  |  |  | 490 | 204.1667
|  |  | Total | 2705 | 1127.0833